## Sheet2
Task |  |  | Hours Spent | Hours Spent | Hours Spent | Hours Spent
|  | Estimated | week 1 | week 2 | week 3 | week 4 | Total
| Role | Hours | 1 | 2 | 3 | 4 | Hours
Integrate Facebook Api | Mohammed Naz/JunedAlam | 5 | 5 | 5 |  |  | 10
Integrate Google Location Services | Mohammad Naz | 10 | 0 | 20 |  |  | 20
Add RecyclerView to Log data to share to FB | Mohammad Naz | 10 | 0 |  | 12 |  | 12
Register Device Sensor to track movement | Mohammad Naz | 10 | 0 |  | 10 |  | 10
Implement Weather API | Mohammad Naz | 15 | 0 |  |  | 14 | 14
Fixed Animation issues | Mohammad Naz | 1 | 0 |  |  | 0.5 | 0.5
Add Front-end changes for UI aesthetics/Material Design | Mohammad Naz | 6 | 0 |  |  | 5 | 5
Add images /share button to recycler view | Mohammad Naz | 2 | 0 |  |  | 2 | 2
Create Login/startup page with smooth UI design | Juned Alam | 2 | 4 |  |  |  | 4
Set Up Firebase for User Registration and Storage | Juned Alam | 5 | 10 |  |  |  | 10
Set up Shared Preferences | Mohammad Naz/Juned Alam | 2 |  |  | 2 |  | 2
Bug Fix- redirect to Location Services Setting | Juned Alam | 2 |  |  | 4 |  | 4
Bug Fix- Layout breaking container/not fitting Screen | Juned Alam | 2 |  |  | 3 |  | 3
Front-End Redesign/add Gradient Color Scheme to Login Page | Juned Alam | 5 |  |  |  | 4 | 4
Use Glide to add Images to RecyclerView from Url | Juned Alam | 3 |  |  |  | 3 | 3
Sensor calibration for accuracy/Project submission Prep | Mohammad Naz/Juned Alam | 2 |  |  |  | 10 | 10
Actual Hours remaining |  | 82 | 63 | 38 | 7 | 0
[8 empty] | Mohammed Naz Hours: | 85.5
Estimated Hours Remaining |  | 82 | 61.5 | 41 | 20.5 | 0 |  | Juned Alam hours: | 45